## Sheet1
EV Loc # | Category# | Department | Comments
Court House | 1 | Recruitment | I was a bit confused on extra staff asigned but it worked out
HEB East 7th | 1 | Recruitment | Number 1 - applicant has to "know" someone to get call
HEB Parmer | 1 | Recruitment | A TOTAL of 3 people would be sufficient.
HEB Parmer | 1 | Recruitment | Better information for workers as to time & names of fellow judges & clerks at individual locations
HEB S. Congress | 1 | Recruitment | 1. I would like to have a single contact with the county for all personnel issues. I got calls from both Davia & Michelle Bybee and sometimes info was not passed between them.
HEB So. Congress | 1 | Recruitment | Don't know about this.
Randall's Lakeway | 1 | Recruitment | 1. not as efficient as when Robin Smith was co-ordinating the deputies & clerks.
RBC | 1 | Recruitment | An exceptionally efficient clerk who has worked with me for several years had a scheduling conflict and would not be aable to work the first six days of early voting. I had hoped to have a substitute for the first six days and have the clerk whom I had worked for as many elections work the last five days. I was disappointed in the decision not to allow this.
Fiesta | 2 | Training | I have worked as a clerk for several years. The setup and break down has not changed. Why do we spend so much time at training sessions going over the same procedures? We need more feedback on things that went wrong or have been changed. Tests are fine only if we are given our scores. How do we know how we did? I was told that I would get my score sent to me to the place where I would be working. I have not heard or seen anything. I believe in learning from our mistakes; but if you don't receive feedback; whats the purpose of a test.
Fiesta | 2 | Training | Some of the trainers (troubleshooters) teaching the EV class for deputies/clerks do not know enough to teach others. Some of the deputies have to help the trainers. The training manuals needs to have the first section of all new or changed items before going into the regular sections in each manual even tho' its been in the past should have the meaning of each abreviated initials etc. JBC, DAU etc. The rest of the manual should have an explanation about something only 1 time in the book, not a dozen different places.
HEB East 7th | 2 | Training | Number 2 - Training equipment was not functioning properly - had to be changed out process took too much time away from training practice.
Mobile | 2 | Training | Rushed at end of training session and not enough time to finish up and to do test review at end
Mobile 2 | 2 | Training | Not enough time to take test after classes
Mobile 3 | 2 | Training | Training was very good, deputy & clerks on mobile 3 were very good to work with.
Mobile 4 | 2 | Training | 2. More specialized training for mobile units
Mobile 4 | 2 | Training | 2. Please a little more specific training for mobile units where we are different from permanant sites.
Randall's Brodie | 2 | Training | Will you please consider the Early Voting workers who work the afternoon shift. These workers have very few choices for these classes that are for training Election Day.
Randall's Research | 2 | Training | This was the most inefficient and disorganized training I have attended from county elections. The printer had no ribbon and had to be replaced. The computer data base had not been cleared and lept showing "Already Voted" on the exercise. We were taken away from valuable trng. to have pictures made. I have no idea how many exercises were planned as we only managed to do 6 and many of those were flawed due to problems with equipment. We spent a lot of time on opening polls even though everyone at my table works the pm shift. Too much time is spent on filling out forms for provisional voters when that is normally done by the deputy. As I say we had hardly completed 6 excercies when we were told to close polls. We were given written test but there was no trng time left to discus the answers and we were told our test would be sent to us with the correct answers. Finally, unlike past trng, no evaluation forms were provided and we specificaly had to request one. Not sure if the county had decided they are not vaulable or did not like what they were hearing. If I had not already known much of this from prior trng and on the job experince I do not think I would be prepared by the trng. Finally, I think the training would be better if done by people who had actually worked at the polls.
| 2 | Training | Machine (pc) was not re-caliabrated so lost valuable time, need to have training for am workers & one for pm workers. As for the training class which I attended we never got around to closing down which is what all @ my table do. They (we) were all pm workers (a team) and only do close down. The spent 45 minutes learning to set up - a waste of our time. All trainers should have to work "in the field" -polling places- before they train. They have no clue what we do. Election day voting is a hassle when the workers have to thumb through 500 pages of "bottom punched" pages. Voters may complain they have to sign over binder rings - but they are 1 person. Workers must thumb through those pages for every voter. So please punch holes in the TOP of the voter list. County must have all equipment ready to go & recalibrated - class time should not be used to reload machinery. County employees - with there attitudes - are costing you very vaulable workers. Soon you will have no experienced workers.
| 2 | Training | Please include a glossary for the acronyms in the training manual. I am a new election worker and found myself wondering what "DAU" or "DRE" meant. Even on the test you gave at my training session you ask a question about the meaning of "EDR". Please give the test results to the participants. Otherwise we don't know our weak areas. At my session I had to leave at 4pm which was the designated quitting time and the results had not been given.
| 2 | Training | During training when test's are taken, info needs to be given at beginning of training, that we will have a test and we will be graded accordingly as to whether we keep our position of deputy or not or other position. It has been done the last couple of elections. Tell us ahead of time. Most of us know exactly what to do when were at the polls the manuals are very clear & the call center is available.
HEB East 7th | 3 | EV Set Up | While I was attending class (training) the troubleshooter was setting up, and I couldn't tell them what we needed. I had to come the next day to set everything up. I had to wait after training for one hour for the troubleshooter to bring me the keys to the trailer.
HEB S. Congress | 3 | EV Setup | 3. Set-up was scheduled for a time when the AM deputy and I were at training.
Mobile | 3 | EV Setup | Some vans delivering to mobile site came on time for setups, but some came late and was very rushed to set-up on time.
Mobile 3 | 3 | EV Set Up | Vans have generally been on time - our judge likes them to come 1 hour before open & they have done so. We miss some of the experienced Trouble-Shooters. Hope pay scale is returned for next election.
Mobile 3 | 3 | EV Set Up | Some days van was late getting to polling site, for set up or pickup.
Mobile 3 | 3 | EV Set Up | Doing better job on arrival times to set up.
Pflugerville | 3 | EV Setup | 1st day setup would have been good except for trouble shooter "Dana Barthlomew" She came in and didn't let us set up. She did most of the work and double checked - she acted like we didn't know what to do - after she left 2 of the e-slates did not work.
Pflugerville | 3 | EV Setup | It took us longer to set up with troubleshooters then us doing it with ourself.
Pflugerville | 3 | EV Setup | We did not need Dana (trainer...?) to help with set up on the first morning she delayed set up got in the way and slowed things down terribly. The crew here is excellent hard working and knowledgable. Everyone did their job well! Thank you!
HEB East 7th | 4 | Signs | #4 Have trouble with distance markers falling off with rain and wind. Suggestion: make signs of metal with weight on bottom.
HEB Parmer | 4 | Signs | Need better signage, voter info,
HEB Parmer | 4 | Signs | #8 Parmer & I35 V. Larger signs needed on property edge to identify & direct voters to this obscure location.
Mobile 4 | 4 | Signs | 4. During voting we need a sign or posting with large bold print thats says "All Travis County Precincts May Vote Here"
Mobile 4 | 4 | Signs | 4. Signs (postings) that say "All Travis County Precincts May Vote Here"
Randall's 35th | 4 | Signs | Need a "Start Here" sign to add behind laptop
HEB East 7th | 5 | Sites | The ramps are old and screws pop-up and are expose. When it rains we can't open the doors.
HEB East 7th | 5 | Sites | Number 5 - no safety cones - no yellow tape - no handrails, cones and tape had to be requested
HEB East 7th | 5 | Sites | 5. We had to request yellow tape for ramps.
HEB Parmer | 5 | Sites | Re: Location of this EV site. Thanks to Schlotzsky's for the use of their restroom facilities after the PM at this site had our porta - can removed. It was probably for the best!
HEB Parmer | 5 | Sites | Not enough instructions in the operations of the generator.
HEB S. Congress | 5 | Sites | 5. The ramps for our trailer are always a problem.
HEB S. Congress | 5 | Sites | 5. Ramps narrow & one w/out guard - no rails & when it rained ramps were slippery & warped when dried. It was 2 days after the call before anyone came.
HEB So. Congress | 5 | Sites | A bit cramped in the mini mobile
Mobile | 5 | Sites | Site selection for mobile sites could have been better. Some of the places selected there was no interest at all. But then the election as a whole up to this point has been very low intrest.
Mobile 2 | 5 | Sites | Need places on mobile that have big crowds of people coming & going like Home Depot. There is no outside participation at assisted living facilities. Heritage was a nursing home facility not able to vote - not good place.
Mobile 3 | 5 | Sites | Most voting sites were easy to find
Mobile 4 | 5 | Sites | It would be better use of the Travis Co. Tax Payers monies to have Early Voting Election Sites located at Grocery Stores, Malls, or other areas where there would be larger numbers of potenial voters. The sites that we were located had sparse people and seemed to be located in out of the way places. If election voting sites were located where people went everyday, ie Walmart, Home Depot, Office Max & etc, there would be greater voter participation.
Pflugerville | 5 | Sites | The reservation of this particular place should be verified and confirmed so the election procedures would not have to "move" as we were told we would have to.
Randall's Lakeway | 5 | Sites | #6 - not enough room for all of the equipment and all the papers we need to have on display for the voters. "Need More Space"
1828 | 6 | Equipment | Radio button too small on laptop for mouse to click on easily.
1828 | 6 | Equipment | Computer buttons should be larger. The demo has too many issues on which to vote takes too long and voters loose interest - eliminate some of the races!
Court House | 6 | Equipment | Phone does not work well in this part of the Court House.
Court House | 6 | Equipment | Cell phone dose not work in Court House.
Court House | 6 | Equipment | Chancy phone
HEB East 7th | 6 | Equipment | We were short one table, didn't have demo delivered at set-up.
HEB S. Congress | 6 | Equipment | Equipment - computer & keyboard very dirty!
HEB S. Congress | 6 | Equipment | PC & Keyboard - are very dirty - need maintanace
HEB SE | 6 | Equipment | Equipment needs more cleaning - key board & screen. Need trash bags -
Mobile 3 | 6 | Equipment | We had trouble with the keyboard, scanner, etc. initially, until - 2 days late- we were told that the mouse had to go in the top port & scanner/keyboard went in the bottom.
Mobile 3 | 6 | Equipment | Had trouble with getting equipment up & running first 2 days.
Randall's 35th | 6 | Equipment | For Demo purposes the Ballot in the Demo DAU is way too long. They lose interest before they get there.
Randall's 35th | 6 | Equipment | Using the DAU at the befinning we are finding the voters can remember by the time they get to the e-slates. The demo should be done before going to the e-slate.
Randall's Ben White | 6 | Equipment | The first day we were short some supplies ie, table clothes, bedsheet ballots, E-slate demo.
Randall's Lakeway | 6 | Equipment | Equipment on set-up was not in perfect condition. Battery on JBC wasn't working properly. Connection that holds cord on printer had only 1 clip.
Mobile 2 | 7 | Forms & Supplies | Didn't have the yellow sheet assistance & oath in supplies
Randall's 35th | 7 | Forms & Supplies | Small bottles of cleaner for the e-slate should be in supply box so we can remove finger prints each morning.
Randall's Lakeway | 7 | Forms & Supplies | Some of the clerks & deputies didn't have badges. It was not made clear that clerks would have photo badges.
1826 | 8 | Procedures | It would be helpful to have specific instructions on timesheets in the manual
Mobile 3 | 8 | Procedures | "Fail-safe Voting" - 1st day - sounds like it will be a real mess for elections - especially if we can't get through to the call center on election day - late in the afternoon.
Pflugerville | 8 | Procedures | To make it easier for the lap-top (Operator,whenever the "flag" for requesting another form of ID the flag on the laptop screen should also show "Add voter to the first Time Voter" listing page.
Randall's Lakeway | 8 | Procedures | Some procedures change after the election has begun.
Randall's S. Mopac | 8 | Procedures | I hope you can eliminate the call-in for change of addresses. It slows things down very much.
HEB So. Congress | 9 | End of Day Closeout | Not applicable
Randall's Ben White | 9 | End of Day Closeout | Item #9 worked morning shift only.
Randall's Ben White | 10 | Call Center | Call center support was marginal one day when we came to work in preparation for 0615 computer boot up. The lap top was not available at the site and all attempts to contact the call center from 0600 -0630 were met with electronic voice mail in lieu of a person. Suggestion: the call center should be open when the sites start opening. No voice mail real people.
Randall's Ben White | 10 | Call Center | Item #10 Required to call, call center prior to 6:30 am each day. Numerous morning no one answered the phone until 7:00 am. Normal procedures phone was answered by voice mail.
HEB Parmer | 11 | Tech Support | Use the same Troubleshooter each day.
HEB Parmer | 11 | Tech Support | The troubleshooters were great & really on top of things.
HEB S. Congress | 11 | Tech Support | 11. One troubleshooter never had a badge even when refered to, he returned I w/ot & said he was never issued one.
Mobile 3 | 11 | Tech Support | Trouble shooters need better maps for directions to polling places.
Randall's Ben White | 11 | Tech Support | The troubleshooters were outstanding during this early voting process.
HEB Parmer | 12 | Election Staff | All the Travis County Staff have been very friendly & helpful too.
HEB S. Congress | 12 | Election Staff | I had trouble with communication with management about workers being hired. Some was good and some wasn't. I am upset about how my situation was handled. What upsets me is one says one thing and then claims they didn't then someone else says I hung up on someone and I didn't. It seems to me that people assumed I would take care of things and I had no power to do that. I would be willing to meet with all parties on what the facts were but not without all present. Michael stated I have problems with management. I really have few problems with management. However, Please quote me correctly, Do not accuse me of things I didn't do and Don't ask me to do anything outside the law. I hope to get along with you in the future. I hope we can have a proper relationship. Sissy Shugrue
HEB So. Congress | 12 | Election Staff | (not including the Deputy for HEB/So. Congress)
1828 | 13 | Misc. | More publicity is definitely needed in order for people to know there is an early voting - and what the election is for! Please try to have our Austin American newspaper "Mag" put this in that daily - plus locations also.
1828 | 13 | Misc. | Several customers commented that the paper did not have the early voting sites listed and therefore did not know where to vote.
Court House | 13 | Misc. | Fine as always
Fiesta | 13 | Misc. | I find every individual involved in any procedures relating to the elections working diligently to preserve the dignity of the election and seeking any method of improvement possible. I am proud of the opportunity to work in Travis County Elections.
Fiesta | 13 | Misc. | Pleas call me.
Fiesta | 13 | Misc. | It would be most helpful (for workers & voters) if in the future similar voting situations, the Secretary of State's Office would provide printed info sheets to hand out to voters at voting locations and early voting locations explaining various senerios. Ex: A vote in primary means one cannot sign petition for independent candidate; also, Primary elections require choosing one party; Nov. election - can vote straight party vote or vote for individual offices regardless of party affiliation.
Fiesta | 13 | Misc. | Concerning the petition for the independent party, we kept getting questions as to whether voters could omit voting for governor and sign petition for Freidman or Strayhorn. In training we were instructed to refer voters to calll the secretary of state # posted. Should this situation occur again is it at all possible to maybe have a printed information sheet available that we could hand out to voters explaining why they can't vote and sign petitions. We have told voters in each situation to refer their questions to the secretary of state and each time were met with strange looks. Maybe it would be worth looking into whether some sort of info sheet or memo could be given to these voters with the secretary of state's number and instructing these voters that if they still had questions to call that number. ??? Just a thought
HEB Parmer | 13 | Misc. | I really enjoyed working w/ the team that was placed with me. This was a fun expeirence plus I learned a lot about voting, I didn't know before.
HEB S. Congress | 13 | Misc. | Although I was hired as an interpreter I was offered the opportunity to receive excellent on the job training (OJT) and hands on training from our deputy Ms. Susan Zillagen. Susan also provided her staff with important voting procedures and emphasized the importance of following the rules and regulations. I enjoyed this experience and comarodery of the group.
HEB S. Congress | 13 | Misc. | Deputy very helpful & availabe & much knowledge. Thank you!
HEB S. Congress | 13 | Misc. | Excellent Deputy in PM
HEB So. Congress | 13 | Misc. | I have worked in many elections, for many years, but never thank goodness worked for anyone like the Deputy at HEB/So. Congress. "Unpleasant" would be an understatement. I have worked as a judge, an alternate judge, and a clerk for many years, but I have never, fortunate, encountered the situation I was placed into. I am very sorry for this woman and I hope she recovers from her ills and accidents. I wish her no ill will, but I do think she needs help. I was continually harrassed and was threatened by her. The things I saw her do and the manner in which she ran this site I have never seen before. It is upsetting to me to write this to you. I thank you for your help and support in this matter. I know it has not been easy for you. I know this does not go on in other voting sites. I hope you can resolve the problems and wish you very good wish. If you would like for me to give you more information, I will. Marie Martin
Mobile 1 | 13 | Misc. | We need better publicity for locations of mobile teams. I'd like to see all locations published daily in the Austin American Statesman. Not everyone has a computer. Encourage mobile loacatins hosts to post voting info. (time - dates, hours) Several days before were there.
Mobile 3 | 13 | Misc. | When I began working Mobile in 2000, the mobile teams got more $ per hour, to compenste for gasoline for long trips. With the price of gas, I'd like to see this policy reinstated.
Mobile 3 | 13 | Misc. | Due to the fact that mobile units depities & clerks travel several miles daliy. I feel they should be compensated more than perment locations. We have to leave home early enough to make sure we are able to find the locations on time. Some places took at least 45 minutes driving in heave traffic.
Mobile 3 | 13 | Misc. | My suggestion would be to pay the mobile team members $1.00 to supplement their gasoline bills, with gasoline prices being so expensive, and some polling places are really quite a distance. Ben Ellis is one of the most efficient Judges we had the pleasure to work with.
Mobile 4 | 13 | Misc. | Ingrid Weigand who works for Austin Energy would like to be contacted prior to our coming to Town Lake Center; 721 Barton Springs Road for the early voting (Mobile 4) so that an in house email/memo will be generated and sent throughout the company so people will know ahead of time about the voting. I talked to some people who said the got the email and some who didn't. At any rate please call this lady about the issue as she says she didn't get the information. Ditto for Leroy Hiller. Also pleas take our addresses and how far we live from polling places into account when making up the schedules. We live near Jonestown & far north and will be traveling far south (ouch)!
Randall's 35th | 13 | Misc. | The Austin American Statesman is not printing the Early Voting locations. We had lots of complaints on that.
RBC | 13 | Misc. | Good set-up and all duties carried out in precise manner. I was happy to work under these conditions as a clerk.
1828 | 14 | VR | When mailing out cards, suggest voters not trim them - they cut off the bar code so they cannot be scanned.